## Sheet1
User Stories
Ref | Story | Size | Complexity | Optimistic | Expected | Persimistic | Factor
1 | Login and Authentication | Large | High | 9 | 13.5 | 18 | 1.5
2 | Dashboard with KPI Indicators | Large | High | 9 | 13.5 | 18 | 1.5
3 | User List With Search Functionality | Medium | Medium | 3 | 6 | 9 | 1
4 | Channel List With Search Functionality | Medium | Medium | 3 | 6 | 9 | 1
5 | Join Channels | Small | Low | 1.35 | 2.7 | 5.4 | 0.9
6 | Private Chat List | Medium | Medium | 3 | 6 | 9 | 1
7 | Joined Channels List | Small | Low | 1.35 | 2.7 | 5.4 | 0.9
8 | Send Private Messages | Small | Medium | 1.5 | 3 | 6 | 1
9 | Send Channel Messages | Small | Low | 1.35 | 2.7 | 5.4 | 0.9
10 | Create Channels | Small | Low | 1.35 | 2.7 | 5.4 | 0.9
Total |  |  |  | 33.9 | 58.8 | 90.6 | 10.6
[8 empty] | Rate Per Hour | 100
|  |  | PERT Expected | 59.95 | 50% | Std Deviation | 9.45 |  | 5995
|  |  | 0.5 | 64.675 | 69.1% |  |  |  | 6467.5
|  |  | 1 | 69.4 | 84.1% |  |  |  | 6940
|  |  | 1.5 | 74.125 | 93.3% |  |  |  | 7412.5
|  |  | 2 | 78.85 | 97.7% |  |  |  | 7885
|  |  | 2.5 | 83.575 | 99.4% |  |  |  | 8357.5
Size Estimations in Hours
Size | Optimistic | Expected | Persimistic
Small | 1.5 | 3 | 6
Medium | 3 | 6 | 9
Large | 6 | 9 | 12
Complexity Estimations
Complexity | Factor
High | 1.5
Medium | 1
Low | 0.9
Standard Deviation and Cumulative Frequencies
Std Dev. | Std Dev Percent | Cumulative. %
0.5 | 19.1% | 19.1%
1 | 15% | 34.1%
1.5 | 9.2% | 43.3%
2 | 4.4% | 47.7%
2.5 | 1.7% | 49.4%
3 | 0.5% | 49.9%